BOARD OF PUBLIC WORKS MEMBERS

KEVIN JAMES

PRESIDENT

HEATHER MARIE REPENNING

VICE PRESIDENT

MICHAEL R. DAVIS

PRESIDENT PRO TEMPORE

JOEL F. JACINTO

COMMISSIONER

LUZ M. RIVAS

COMMISSIONER

FERNANDO CAMPOS

EXECUTIVE OFFICER

Ignacio Rodriguez, Project Manager Green Building Corporation

6913 Alcove Ave

North Hollywood, CA 91605

CITY OF LOS ANGELES

CALIFORNIA

ERIC GARCETTI

MAYOR

September 06, 2017

DEPARTMENT OF PUBLIC WORKS BUREAU OF ENGINEERING

GARY LEE MOORE, PE, ENV, SP

CITY ENGINEER

1149 S. BROADWAY, SUITE 700 LOS ANGELES, CA 90015-2213

http://eng.lacity.org

Project:  Temescal Canyon Park Ph II Project		W.O. EW40029F Subject: Emergency AO No. 02-003	CLA Ltr. No.02-003

Dear Ignacio Rodriguez:

You are directed to proceed with the work as described in Emergency AO No. 02-003, attached. Also, please provide a lump sum proposal for the allowance order work with a complete itemized cost breakdown of all labor, materials and equipment , while continuing to perform the allowance order work. Please submit your written cost proposal within two weeks from the date of this letter. This office will review your proposal and, if necessary, it will be negotiated for final resolution to the satisfaction of both parties.

In addition, please provide a CPM schedule analysis for any impact to the critical path of the construction schedule as a result of this allowance order work. If applicable, provide an estimate in terms of calendar days, supported by the analysis, to be added or deducted from the critical path of the current project schedule.

Except as indicated otherwise, all work related to this Allowance Order shall be done in accordance with applicable portions of the original contract documents.

For all correspondence regarding this change, please reference Emergency AO No.02-003. If you have any questions, please contact at () -.

Sincerely,

Anagh Mamdapurkar Construction Manager

Construction Management Division cc: Greg.Snyder@lacity.org

AN EQUAL EMPLOYMENT OPPORTUNITY EMPLOYER	Recyclable and made from recycled waste.

City of Los Angeles - Department of Public Works - Bureau of Engineering

EMERGENCY ALLOWANCE ORDER

| Project Title Temescal Canyon Park Ph II Project |  |  | Project No O/01-54 | EAO No 003 | File No 8.5.5 | Page No |
| --- | --- | --- | --- | --- | --- | --- |
| W.O. No EW40029F | Contract No C-127470 | Bid Item No 02 | Subject Provide Service Contract to Clean Sediments in Underground Tank |  |  |  |
| Contractor Green Building Corporation |  | AOR No 005 | Plan Reference C-02 |  |  |  |
| Schedule Activity |  |  | Specification Reference N/A |  |  |  |

- Reason for Allowance Order

The Underground Storage Tank constructed in Phase I contains 12" to 18" of wet sediments. Sediments must be removed to allow for installtion of equipment inside the Tank.

This is an unforeseen condition.

BOE held on site meeting with GBC and their proposed service contractor United Pumping.  Sediments were sampled and a proposal was provided for daily rates to remove sediments (attached).

- Description of Allowance Order

Proceed with removal of sediments as per the 8/31/2017 propsoal from GBC/United Pumping. Work shall proceed on T&M basis with Not to Exceed 6 days of cleaning or $83,269.

Allowance Line Item 2 has $62,318 remaining unused.  If the value of this T&M Allowance Order exceeds this amount, then BOE will issue a Change Order to compensate Contractor for the balance of the actual cost.

Pumping and removal of sediments to be performed by United Pumping - a Service Contractor to GBC.

Prior to start of work, Contractor shall arrange a kick off meeting with GBC, United Pumping, BOE and Con Ad to discuss monitoring of the this T&M process.

- Allowance Order Amount

Total amount of this Allowance Order shall not exceed $75,000.00.

The Contractor shall keep track of the costs, notify the Engineer in writing when the costs approach 50% and 75% of the not-to-exceed amount, and obtain approval from the Engineer before proceeding with any work that will exceed the stated amount. Final compensation will be based upon documented daily labor, material, and equipment costs to complete the scope of work defined above (if the change order is performed on a time & material basis), or on a lump sum basis (if the change order is negotiated full and final), and will be included in the final Allowance Order.

- Change in Contract Duration

Schedule adjustment will be based upon documented impact to the project schedule, and will be included in the final Change Order

Submitted By:		Anagh Mamdapurkar	Date:	09/06/2017

Construction Manager

Approved By:		Katherine Doherty	Date:	09/06/2017

Project Manager/Sr. Construction Manager

Approved By:		Iftekhar Ahmed	Date:	09/06/2017

Sr.Engineer / Division Manager

Approved By:		Ignacio Rodriguez	Date:	09/28/2017

Contractor

| Uploaded Files |  |  |
| --- | --- | --- |
| File Name COR 18-R1.pdf | Size(Bytes) 965546 | Uploaded By Anagh Mamdapurkar |

Document links

AO Initiation	2-003: Clean Sediments in Underground Tank

CM AO Est	006-R00 - AO 2-003: Provide Service Contract to Clean Sediments in Underground Tank