BOARD OF PUBLIC WORKS MEMBERS

KEVIN JAMES

PRESIDENT

HEATHER MARIE REPENNING

VICE PRESIDENT

MICHAEL R. DAVIS

PRESIDENT PRO TEMPORE

JOEL F. JACINTO

COMMISSIONER

AURA GARCIA

COMMISSIONER

DR. FERNANDO CAMPOS

EXECUTIVE OFFICER

Nicholas Ohashi, Project Manager Sully-Miller Contracting Co.

, CA

CITY OF LOS ANGELES

CALIFORNIA

ERIC GARCETTI

MAYOR

March 13, 2018

DEPARTMENT OF PUBLIC WORKS BUREAU OF ENGINEERING

GARY LEE MOORE, PE, ENV, SP

CITY ENGINEER

1149 S. BROADWAY, SUITE 700 LOS ANGELES, CA 90015-2213

http://eng.lacity.org

Project: Albion Riverside Park Project	W.O. EW40060F / E1907621 Subject: Fully Executed Final T&M AO No. 03-006		CLA Ltr. No.03-006

Dear Nicholas Ohashi:

Transmitted herewith is fully executed Final T&M AO No.03-006 for your records.

You may proceed to submit this allowance order to the Project Inspector with your next monthly progress payment.

For all correspondence regarding this change, please reference Final T&M AO No. 03-006. If you have any questions, please contact me at (213) 485-1632.

Sincerely,

Neel Mistry Construction Manager

Prop O Clean Water Division

Click here to view Allowance Order Agreement Letter

cc: Jose.fuentes@lacity.org, angela.martinez@lacity.org, Charles.Gannon@lacity.org, lee.williamson@lacity.org, bryan.powell@lacity.org

AN EQUAL EMPLOYMENT OPPORTUNITY EMPLOYER	Recyclable and made from recycled waste.

City of Los Angeles - Department of Public Works - Bureau of Engineering

FINAL TIME & MATERIALS ALLOWANCE ORDER

| Project Title ALBION RIVERSIDE PARK PROJECT |  |  | Project No EW40060F | FTMAO No 006 | File No 8.5.11 | Page No |
| --- | --- | --- | --- | --- | --- | --- |
| W.O. No EW40060F / E1907621 | Contract No 0 | Bid Item No 03 | Subject Metal Debris at Gallery #4 |  |  |  |
| Contractor Sully-Miller Contracting Co. |  | AOR No 001 | Plan Reference C-21 Grid E-6 |  |  |  |
| Schedule Activity IF-4000 |  |  | Specification Reference 02310 |  |  |  |

- Reason for Allowance Order

During the excavation of Infiltration Gallery #4, a large amount of sheet metal and metal shavings were found buried 2 feet below the surface within an area of approximately 20' by 40'.

Note: It is not possible to perform the excavation of this area with the scrapers until the debris is removed.

- Description of Allowance Order

This Final T&M AO compensates the Contractor for the removal and disposal of metal debris which was encountered during the excavation of Infiltration Gallery #4.

The Contractor submitted T&M sheets for the period 01/16/2018 to 01/17/2018 to document its daily labor, material and equipment costs to complete the scope of work defined above.The T&M sheets were approved and signed by the BCA Inspector and verified by the Engineer, see attachment.

The Contractor shall reflect the above changes on the project As-Built drawings.

- Allowance Order Amount

Extra Work - Time and Materials Price                                                                  ADD $48,349.00

Allowance Bid Item Summary

| Original Allowance Bid Item Amount | $300,000.00 |
| --- | --- |
| Previous Approved Allowance Order | $0.00 |
| This Allowance Amount | $48,349.00 |
| Remaining Balance of Allowance | $251,651.00 |

The compensation set forth in this Allowance Order comprises the total compensation due the CONTRACTOR, all Subcontractors, and all Suppliers, for the work defined in this Allowance Order, including impact on the unchanged work. By signing the Allowance Order, the CONTRACTOR acknowledges and agrees on behalf of himself, all Subcontractors, and all Suppliers, that the stipulated compensation includes payment for all work contained in the Allowance Order, plus all payment interruptions of schedules, extended field overhead costs, delay, and all impact, ripple effect or cumulative impact on all other work under this Contract. The signing of the Allowance   Order indicates that the Allowance Order constitutes full mutual accord and satisfaction for the work, and that the cost under the Allowance Order constitutes the total equitable adjustment owed the CONTRACTOR, all Subcontractors, and all Suppliers. The CONTRACTOR on behalf of himself, all Subcontractors, and all Suppliers, agrees to waive all rights, without exception or reservation whatsoever to file any further claim related to this Allowance Order.

Submitted By:		Neel Mistry		Date:	02/28/2018

Construction Manager

Approved By:		Bryan Powell		Date:	02/28/2018

Project Manager

Approved By:		Maurico Arreola		Date:	03/13/2018

Contractor

Approved By:

Jose Fuentes		Date:	03/13/2018

Sr.Engineer / Division Manager

| Uploaded Files File Name | Size(Bytes) | Uploaded By |
| --- | --- | --- |
| AO 3-006 Metal Debris T&M Signed 01162018.pdf 7078310 |  | Neel Mistry |
| AO 3-006 Metal Debris T&M Signed 01172018.pdf 7104452 |  | Neel Mistry |
| AO3-006 - CM Estimate Rev1.pdf | 4216231 | Neel Mistry |
| METAL DEBRIS PHOTO 1.jpg 3137242 |  | Neel Mistry |
| METAL DEBRIS PHOTO 2.jpg 5911794 |  | Neel Mistry |
| METAL DEBRIS PHOTO 3.jpg 6600630 |  | Neel Mistry |

Document links

AO Initiation	3-006: Metal Debris at Gallery #4 AO Record Of

Negotiation	3-006: Metal Debris at Gallery #4

AO Request	AOR 001 -TMAO 3-006 Subject: Metal Debris at Gallery #4 CM AO Est	001-R00 - AO 3-006: Metal Debris at Gallery #4

Requests for

Information (RFIs)

Time & Materials

0038 - Buried Metal Waste

AO	3-006: Metal Debris at Gallery #4