City of Los Angeles - Department of Public Works - Bureau of Engineering

UNILATERAL ALLOWANCE ORDER

| Project Title PENMAR WATER QUALITY IMPROVEMENT PROJECT PHASE II |  |  | Project No O/01-53 | UAO No 009 | File No 8.5.10 | Page No |
| --- | --- | --- | --- | --- | --- | --- |
| W.O. No EW40028F | Contract No C-127429 | Bid Item No 03 | Subject Extend Electrical Ductbank on Rose Ave |  |  |  |
| Contractor Green Building Corporation |  | AOR No None Specified | Plan Reference E-01 |  |  |  |
| Schedule Activity |  |  | Specification Reference |  |  |  |

- Reason for Allowance Order

While trenching for the installation of the electrical ductbank along Rose Ave, the Contractor uncovered the existing 80” RCP storm drain pipe shown on Drawings C-01 & C-03. The actual location of the RCP (further west than shown) is where the new ductbank turns north toward the golf course connection.  This condition leaves insufficient clearance to run the new ductbank between the existing 80" RCP pipe and the 30” & 12” concrete encased pipeline installed under Phase 1. To facilitate the installation, the ductbank needs to be extended further west (about 8 feet) in the same alignment of the extended 16" treated water line.

Note: This allowance order was previously issued as EAO 3-009 on June 6, 2017, which the Contractor refused to sign. As such, it is being re-issued as a Preliminary Allowance Order in order to proceed with the issuance of a Unilateral Allowance Order.

- Description of Allowance Order

Contractor shall provide labor, material, and equipment to extend the ductbank, as-needed, to clear the existing 80" RCP storm drain pipe, as shown, on the attached marked-up Contract Drawing E-01.

All work shall be performed in full compliance with the contract documents.

Note: BOE and GC agree on the cost, but not the time impacts of this extra work.

- Allowance Order Amount

Extra Work - Lump Sum Unilateral Price	ADD $8,582.00

Allowance Bid Item Summary

Original Allowance Bid Item Amount	$50,000.00

Previous Approved Allowance Order	$25,157.00

This Allowance Amount	$8,582.00

Remaining Balance of Allowance	$16,261.00

The compensation (time and cost) set forth in this Allowance Order comprises the total compensation due the CONTRACTOR, all Subcontractors, and all Suppliers, for the work or change defined in this Allowance Order, including impact on the unchanged work. By signing the Allowance Order, the CONTRACTOR acknowledges and agrees on behalf of himself, all Subcontractors, and all Suppliers, that the stipulated compensation includes payment for all work contained in the Allowance Order, plus all payment interruptions of schedules, extended field overhead costs, delay, and all impact, ripple effect or cumulative impact on all other work under this Contract. The signing of the Allowance Order indicates that the Allowance Order constitutes full mutual accord and satisfaction for the change, and that the time and cost under the Allowance Order constitutes the total equitable adjustment owed the CONTRACTOR, all Subcontractors, and all Suppliers, as a result of the change. The CONTRACTOR on behalf of himself, all Subcontractors, and all Suppliers, agrees to waive all rights, without exception or reservation of any whatsoever to file any further claim related to this Allowance Order. No further claim or request for equitable adjustment of any type shall rise out of or as a result of this Allowance Order or the impact of this Allowance Order on the remainder of the work under this Contract.

Submitted By:		Waleed Azar		Date:	10/12/2017

Construction Manager

Approved By:		Katherine Doherty		Date:	10/16/2017

Project Manager

Approved By:		UNILATERAL		Date:

Contractor

Approved By:

Jose Fuentes		Date:	10/16/2017

Sr.Engineer / Division Manager

Uploaded Files

File Name	Size(Bytes)	Uploaded By

AOI - Extend ductbank west

on Rose Ave.pdf	1348612	Waleed Azar

PAO 009 - COR 024 -

Negotiated for Time Not Cost.pdf

12610744	Waleed Azar

Document links

Change Order	020: Resolution of Unilateral Change Orders, Allowance Orders and All Disputed Issues

CM CO Est	020-R00 - CO-020: Resolution of Unilateral Change Orders, Allowance Orders and All Disputed Issues CO Initiation	020: Resolve Unilateral Change and Allowance Orders, and All Disputed Issues

CO Record of

Negotiation	020: Resolution of Unilateral Change Orders, Allowance Orders, and All Disputed Issues

Preliminary CO	020: Resolve Unilateral Change Orders and Allowance Orders and All Disputed Issues