Attachment 25.1.4

Page 1 of 1

CONSTRUCTION CONTRACT CLOSEOUT PROCEDURE STATEMENT OF COMPLETION FLOWCHART

2	LI

DISTRIBUTE TO: CM, LI, PM, CONTR

PREPARE “NOTICE TO FINAL”

ESTABLISH TARGET DATE DETERMINE CRITICAL ITEMS ANNOTATE CORRECTION LIST

5 DAYS

1	CONTR

3	LI/PI

5	FI

12

FI

PREPARE & SIGN SC FOR IPW & FORWARD TO CM

| 9 CM/LI/PM 8 | CM/LI/PM |  |
| --- | --- | --- |
| RE-INSPECT WORK |  |  |
| 1 DAY / 21 - 36 |  |  |

| 11 | LI |  |
| --- | --- | --- |
| NOTIFY FI |  |  |
| 1 DAY / 23 - 38 |  |  |

| 13 | CM |  |
| --- | --- | --- |
| OBTAIN DE SIGNATURE & DISTRIBUTE SC |  |  |
| 3 DAYS / 29 - 44 |  |  |

REQUEST FOR FINAL INSPECTION

3 DAYS / 14

NOTIFY PI & FI FOR FINAL INSPECTION

PERFORM INSPECTION & DISTRIBUTE CORRECTION LIST

APPROVE WORK

SC ACCOMPLISHED

YES

3 DAYS / 26 - 41

1 DAY / 1

1 DAY

1 DAY / 22 - 37

| DISTRIBUTE TO: 6 | CM/LI/PM |  |
| --- | --- | --- |
| COORDINATE WITH CONTR |  |  |
| 1 DAY / 15 |  |  |

| 7 | CONTR |  |
| --- | --- | --- |
| COMPLETE CORRECTION LIST ITEMS AND ADVISE LI |  |  |
| 5-20 DAYS / 20-35 |  |  |

| 4 | FI |  |
| --- | --- | --- |
| SCHEDULE FINAL INSPECTION & NOTIFY LI |  |  |
| 10 DAYS / 11 |  |  |

| NO |  |  |
| --- | --- | --- |
|  | 10 | LI |
|  | NOTIFY CONTR TO CORRECT |  |
|  | 1 DAY / 22 - 37 |  |

LI, PD, CONTR & FILE

ACRONYMS

BCA BOE BPW CM CR

CONTR DE

FI GS IPW LI LD NOI OCC OOA PC PCR PI PM SM SC SPC

DESCRIPTION

BUREAU OF CONTRACT ADMINISTRATION BUREAU OF ENGINEERING

BOARD OF PUBLIC WORKS CONSTRUCTION MANAGER COMPLETION RECOMMENDATION CONTRACTOR

DIVISION ENGINEER FINAL INSPECTOR

GENERAL SERVICES (BCA) INSPECTOR OF PUBLIC WORKS LEAD INSPECTOR

LIQUIDATED DAMAGE NOTICE OF INTENT

OFFICE OF CONTRACT COMPLIANCE OFFICE OF ACCOUNTING

PARTIAL COMPLETION

PARTIAL COMPLETION RECOMMENDATION PRINCIPAL INSPECTOR

PROJECT MANAGER

BUREAU OF SANITATION MANAGER STATEMENT OF COMPLETION STATEMENT OF PARTIAL COMPLETION

SC_FINAL_20060803

1 of 1