Attachment 25.1-6

Page 1 of 1

CONSTRUCTION CONTRACT CLOSEOUT	PROCEDURE RETENTION RELEASE, AS BUILT, & ACCEPTANCE FLOWCHART

| 60 DAYS FOR COMPLETION 3 | BCA/GS |  |
| --- | --- | --- |
| PREPARE ESTIMATE OF WITHHOLIDNG |  |  |
| 3 DAYS / 29 |  |  |

| 4 | BCA/GS |  |
| --- | --- | --- |
| RELEASE RETENTION TO ACCOUNTING |  |  |
| 1 DAY / 30 |  |  |

| 5 | OOA |
| --- | --- |
| RELEASE RETENTION TO CONTR |  |
| 30 DAYS/ 60 |  |

1	CM

2	LI

ISSUE FINAL CLOSEOUT CHANGE ORDER

PREPARE FINAL PROGRESS PAYMENT

23 DAYS / 23

3 DAYS / 26

| 6 | CM |  |
| --- | --- | --- |
| RECEIVE MARK-UP’S (FROM CONTR.) |  |  |
| 1 DAYS / 1 |  |  |

| 7 | CM |  |
| --- | --- | --- |
| VERIFY MARKUP ACCURACY |  |  |
| 7-30 Days/ 8 - 31 |  |  |

| 8 | CM |  |
| --- | --- | --- |
| INCORPORATE COMMENTS |  |  |
| 30-60 DAYS/ 38 -91 |  |  |

| 9 | CM |  |
| --- | --- | --- |
| OBTAIN SIGNATURES & SUBMIT TO PLAN PROCESSING (VAULT) |  |  |
| 7-14 DAYS/ 45 - 105 |  |  |

| 10 | RM/CM |  |
| --- | --- | --- |
| VERIFY AS-BUILTS ARE UPLOADED TO NAVIGATE LA |  |  |
| 7-30 DAYS/ 54 - 135 |  |  |

11	BCA

14	BCA/BOE/OCC

15	BPW

SC ACCOMPLISHED

PREPARE DRAFT BOARD REPORT

PREPARE, APPROVE & SIGN OFF FINAL BOARD REPORT

ACCEPT PROJECT

YES

7 DAYS / 7

7 DAYS / 38

7 DAYS / 45

| NO |  |  |  |
| --- | --- | --- | --- |
| 12 | BOE/OCC |  |  |
| REVIEW DRAFT BOARD REPORT & RECOMMEND LD’S & PENALTIES (IF NECESSARY) |  |  |  |
| 21 DAYS / 28 |  |  |  |

| 13 | BOE/OCC |  |
| --- | --- | --- |
| APPROVE & INITIAL DRAFT BOARD REPORT |  |  |
| 3 DAYS / 31 |  |  |

| 20 | CM |
| --- | --- |
| CLOSE WORK ORDER |  |
| 3 DAYS / 135 |  |

| 16 | CA/BOE/BCA |  |
| --- | --- | --- |

| 19 | CONTR |  |
| --- | --- | --- |

ANY LEGAL ISSUES?

18	BCA/BOE

ACRONYMS

SUBMIT FINAL SUBCONTRACTING REPORT & CERTIFIED PAYROLLS

BCA BOE BPW CM CR

CONTR

DESCRIPTION

BUREAU OF CONTRACT ADMINISTRATION BUREAU OF ENGINEERING

BOARD OF PUBLIC WORKS CONSTRUCTION MANAGER COMPLETION RECOMMENDATION CONTRACTOR

YES

17	CA/BOE/BCA

RECOMMEND RETENTION WITHHOLDING

28 DAYS

PREPARE CONTR

PERFORMANCE EVALUATION REPORTS

7 DAYS

NO

7 DAYS

POSSIBLE (T=INFINITY)

DE FI GS IPW LI LD NOI OCC OOA PC PCR PI

SM SC SPC

DIVISION ENGINEER FINAL INSPECTOR

GENERAL SERVICES (BCA) INSPECTOR OF PUBLIC WORKS LEAD INSPECTOR

LIQUIDATED DAMAGE NOTICE OF INTENT

OFFICE OF CONTRACT COMPLIANCE OFFICE OF ACCOUNTING

PARTIAL COMPLETION

PARTIAL COMPLETION RECOMMENDATION PRINCIPAL INSPECTOR

BUREAU OF SANITATION MANAGER STATEMENT OF COMPLETION STATEMENT OF PARTIAL COMPLETION

Retention Release FINAL 20060803

1 of 1