Attachment 24.1-2

Responsibility: Startup Team Leader and Startup Team

[  ] Review project/facility design.  Meet with Project Manager, Project Engineer and Construction Manager.

[  ]  Assemble Startup Team.

[  ]  Team review project/facility basis of design, description and contract documents.

[  ] Introduce startup Team to Contractor.

[  ]  Review Contractor submittals and witness Factory Testing.

[  ] Review Shop Performance Test Reports.

[  ] Prepare and submit comments on Contractor Startup Schedule to CM.

[  ]  Verify/witness proper installation of equipment.

[  ]  Review Contractor’s preliminary instrument Calibration Forms, Alignment Data Forms, Vibration Analysis Forms, Equipment Checkout Forms, Electrical Test Results, and Noise Analysis Data Forms.

[  ] Prepare and submit comments on preliminary instrument Calibration Forms, alignment Data Forms, Vibration Analysis Forms, Equipment Checkout Forms, Electrical Test Results and Noise Analysis Data Forms to CM.

[  ]  Review Contractor’s Draft O&M Manual and MSDS Yellow Book.

[  ] Prepare and submit comments on Draft O&M Manual and MSDS Yellow Book to CM.

[  ] Review Contractor’s Draft Recommended Spare Parts Lists.

[  ]  Prepare and submit comments on Contractor’s Draft Recommended Spare Parts Lists to CM.

[  ] Review Contract’s Draft O&M Training Plan.

[  ] Prepare and submit comments on Contractor’s Draft O&M Training Plan to CM.

[  ]  Review Contractor’s Draft O&M Training Materials.

Page 1 of 3

Attachment 24.1-2

Responsibility: Startup Team Leader and Startup Team

[  ] Prepare and submit comments on Contractor’s Draft O&M Training materials to CM.

[  ] Coordinate Contractor’s O&M Training with Owner/Client.

[  ] Review Draft Phase 1 Operational Readiness Test procedures and forms.

[  ] Prepare and submit comments on Draft Phase I Operational Readiness Test procedures and forms to CM.

[  ] Verify/witness Draft Phase 1 Operational Readiness Tests.

[  ] Review Draft Functional Test procedures.

[  ] Prepare and submit comments on Draft Phase II Operational Readiness Test procedures and forms to CM.

[  ] Verify/witness Draft Phase II Operational Readiness Tests.

[  ] Review Draft Functional Test procedures.

[  ] Prepare and submit comments on Draft Functional Test procedures to CM.

[  ] Verify/witness Functional Test of Unit processes and sub-units.

[  ] Review Draft Facility Performance Test and Performance Acceptance Test Plan.

[  ]  Prepare and submit comments on Draft Facility Performance Test and

Performance Acceptance Test Plan to CM.

[  ] Define Performance Acceptance Test Criteria.

[  ] Prepare Performance Acceptance Test Data Collection Form(s).

[  ] Assemble Startup Team and Owner/Client staff for facility Performance Test.

[  ] Prepare and submit Startup Team and Owner/Client staff roster for Facility

Performance Test to CM.

[  ] Prepare Performance Acceptance Test sampling and laboratory analysis schedule.

Page 2 of 3

Attachment 24.1-2

Responsibility: Setup Team Leader and Startup Team

[  ] Submit Performance Acceptance Test sampling and analysis schedule to laboratory.

[  ] Verify/witness Facility Performance Test including Performance Acceptance Test.

[  ] Evaluate Facility Performance Test including Performance Acceptance Test.

[  ] Prepare and submit comments on Facility Performance Acceptance Test Reports

Acceptance Test data to CM.

[  ] Review Facility Performance Test and Performance Acceptance Test Reports.

[  ] Prepare and submit comments on Facility Performance Test and Performance

Acceptance Test Reports to CM.

[  ] Prepare and submit list of facility deficiencies to CM.

[  ] Prepare and submit Punch List items to CM.

[  ] Coordinate Startup Assistance activities with CM, Owner/Client, and Contractor.

Page 3 of 3