Attachment 24.1-4

Responsibility: Owner/Client

[  ] Review Startup Schedule.

[  ] Prepare and submit comments on Draft O&M Manual and MSDS Yellow Book to Startup Team.

[  ] Prepare and submit comments on Recommended Spare Parts List to Startup Team.

[  ]  Prepare and submit comments on Draft O&M Training Plan to Startup Team.

[  ] Prepare and submit comments on Draft O&M Training Materials to startup Team.

[  ] Attend and receive O&M Training.

[  ] Verify/witness Functional Test of unit processes and sub-units.

[  ] Review and submit comments on Final Facility Performance Test and Performance Acceptance Test Plan.

[  ] Assemble staff for Final Facility Performance Test and Performance Acceptance

Test.

[  ] Coordinate interface with Contractor during Facility Performance Test and Performance Acceptance Test.

[  ]  Submit Performance Acceptance Test sampling and analysis schedule to laboratory.

[  ] Verify/witness Facility Performance Test and Performance Acceptance Test.

[  ] Prepare and submit Punch list items to CM.

[  ] Accept Recommended Spare Parts delivery(ies).

[  ] Begin Beneficial Occupancy.

Page 1 of 1