Attachment 24.1-5

Responsibility: Contractor

[  ] Prepare Startup Schedule.

[  ] Issue Notice of Startup Schedule.

[  ]  Install equipment.

[  ] Prepare and submit Preliminary Instrument Calibration Forms, Alignment Data Forms, Vibration Analysis Forms Equipment Checkout Forms, Electrical Test Forms, and Noise Analysis data Forms.

[  ] Prepare and submit Final Instrument Calibration Forms, Alignment Data Forms, Vibration Analysis Forms, Equipment Checkout Forms, Electrical Test Forms, and Noise Analysis data Forms.

[  ] Prepare and submit draft O&M Manuals and MSDS Yellow Book.

[  ] Prepare and submit Final O&M Manuals and MSDS Yellow Book.

[  ] Prepare and submit Draft Recommended Spare Parts List.

[  ]  Prepare and submit Final Recommended Spare Parts List.

[  ] Begin Recommended Spare Parts purchase and delivery.

[  ] Prepare and submit Draft O&M Training Plan.

[  ] Prepare and submit Final O&M Training Plan.

[  ] Prepare and submit Draft O&M Training Materials.

[  ] Prepare and submit Final O&M Training Materials.

[  ]  Provide O&M Training to Owner/Client.

[  ] Prepare Draft Phase I Operational Readiness Test procedures and forms.

[  ] Prepare Final Phase I Operational Readiness Test procedures and forms.

[  ] Perform Phase I Operational Readiness Test.

[  ] Prepare Draft Phase II Operational Readiness test procedures and forms.

Page 1 of 3

Attachment 24.1-5

Responsibility:  Contractor

[  ]  Prepare Final Phase II Operational Readiness Test procedures and forms.

[  ] Perform Phase II Operational Readiness Test.

[  ] Prepare draft Functional Test procedures and forms.

[  ] Prepare Final Functional Test procedures and forms.

[  ] Perform Functional Test of unit processes and sub-units.

[  ] Prepare and submit Draft Facility Performance Test and Performance Acceptance Test Plans.

[  ]  Procure fuels, lubricants, and chemicals for Facility Performance Test including, Performance Acceptance Test.

[  ] Prepare and submit Facility Performance Test Rosters, including Performance Acceptance Test.

[  ] Assemble Contractor/Manufacturer/Vendor staff for Facility Performance Test, including Performance Test.

[  ] Perform Facility Performance Test including Performance Acceptance Test.

[  ] Prepare and submit Draft Facility Performance Test and Performance Acceptance Test Reports.

[  ] Prepare and submit Final Facility Performance Test and Performance Acceptance Test Reports.

[  ]  Complete correction of Punch List items.

[  ] Correct deficiency(ies) described in Notice(s) of Deficiency(ies) and Notice (s) to Correct.

[  ] Request Final inspection.

[  ] Complete Recommend Spare Parts Purchase and delivery.

Page 2 of 3

Attachment 24.1-5

Responsibility: Contactor

[  ] Provide Equipment Warranties and Guaranties.

[  ] Initiate warranty period.

[  ] Initiate Startup Assistance period

Page 3 of 3